## certificate
Quaterly Progress Report - FIP Till date 31.12.2024
Name of the Watershed : LURGHUTI |  |  |  | Total Treatable Area : | 1027.29
District / Block : SIDHI/KUSMI
Name of the VWC : Watershed Committee LURGHUTI |  |  |  | NGO : GRAM SUDHAR SAMITI
Total Project Cost |  | 20042102
Community Contribution |  | 1067806
Sanctioned Grant |  | 18620856
Total Grant Released :- |  | 14766369
Total Unutilized grant as on reporting date: 31.12.2024 |  | 816056
Amt in Rs
Sr No. | Grant Status | Project Implementation |  | Project Management |  | Total
|  | NABARD | CSR | NABARD | CSR
1 | Grant Sanctioned | 15507782 | 0 | 3113074 | 0 | 18620856
2 | Grant received during the current quarter | 0 | 0 | 0 | 0 | 0
3 | Grant received till the end of previous quarter | 12423047 | 0 | 2343322 | 0 | 14766369
4 | Cumulative Grant received | 12423047 | 0 | 2343322 | 0 | 14766369
5 | Grant utilised till the end of current quarter | 1458237 | 0 | 151978 | 0 | 1610215
6 | Grant utilised till the end of previous quarter | 10148754 | 0 | 2191344 | 0 | 12340098
7 | Cumulative Grant utilised | 11606991 | 0 | 2343322 | 0 | 13950313
8 | Balance of Grant carried forward to next quarter | 816056 | 0 | 0 | 0 | 816056
a. | Physical & Financial progress
b. | Cumulative Labor Payment | 3728282
c. | Supervision payment | 373940
d. | Cum.Community contribution | 788350
e. | Shramdan %age (d/(b+d) X100 | 17.45%
Certificate
Certified that :-
a. | Except for the deviations mentioned on a separate sheet, area treatment mention
this progress report have been carried out
according to the technical norms prescribed in sanctioned document and the condition of sanction.
VWC president & secretary along with Team leader of project must sign all the pages
Sign of Watershed Secreatry (For Area Treatment)
Name - Rajbahadur Singh
b. | The items of expenditure mentioned in this progress report are suppot by proper
documents and proper records and book of accounts have been maintained for the same.
The statement and data presented in this report are true to the best of our knowledge.
| For the Village Watershed Committee |  |  |  | For the NGO
| Name - Rambahadur Singh |  |  |  | Name - Brijendra Mishra
| Designation - President |  |  |  | Designation - Secreatry
| Place - Lurghuti |  |  |  | Place - Sidhi
| Date - 31.12.2024 |  |  |  | Date - 31.12.2024

## achievemnt
Name of Watershed: LURGHUTI Watershed Name of NGO: GRAM SUDHAR SAMITI
Details of funds |  | 1) Funds received for project treatment till date (Rs) : |  |  |  |  | 14766369
|  | 2) Amount spent till date (Rs) : |  |  |  |  | 13950313
|  | 3) Balance amount as on date (Rs) : |  |  |  |  | 816056
S. No | Treatment | Grant Sanctioned | [10 empty] | Cum. Achievement upto last reporting period |  |  |  |  | Achievement during current reporting period | [6 empty] | Cum. Achievement
|  | Unit cost (Rs) | Area (ha) | Phy. (CuM / No.) | Phy. (CuM / No.) | Labour | Supervision | Material | Cost (Rs) | Community contibution (16% of the col l in Rs) | Cash Contribution | Grant Amount (in Rs.) | Area/unit completed (Cum) | Labour | Material | Supervision | Total expenditure | Area/unit (Cum.) |  | Labour | Material | Supervision | Total expenditure | Area (ha) | Area/unit completed | Labour | Material | Supervision | Total expenditure
[18 empty] | completed | In prog.
A | Area Treatments
1 | Farm Pond (FP) | 221967.3 |  | 10 | 10 | 2092921 | 0 | 126752 | 2219673 | 334867 | 0 | 1884806 | 10 | 1753534 | 131270 | 0 | 1884804 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10 | 1753534 | 131270 | 0 | 1884804
2 | Staggerd Contour Trench (SCT) | 164.533 |  | 750 | 750 | 119400 | 0 | 4000 | 123400 | 19104 | 0 | 104296 | 750 | 100248 | 4000 | 0 | 104248 | 0 | 0 | 0 | 0 | 0 | 0 |  | 750 | 100248 | 4000 | 0 | 104248
3 | Farm Bund (FB) | 156.7894 |  | 19 | 2280 | 349980 | 0 | 3000 | 352980 | 55997 | 0 | 296983 | 19 | 293940 | 3000 | 0 | 296940 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19 | 293940 | 3000 | 0 | 296940
4 | Plantation (Agroforestry) | 54.4 |  | 1600 | 1600 | 28240 | 0 | 58800 | 87040 | 4518 | 0 | 82522 | 1750 | 23685 | 58770 | 0 | 82455 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1750 | 23685 | 58770 | 0 | 82455
5 | Plantation (Horticulture) | 79.338 |  | 1600 | 1600 | 42140 | 0 | 84800 | 126940 | 6742 | 0 | 120198 | 1620 | 35392 | 84040 | 0 | 119432 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1620 | 35392 | 84040 | 0 | 119432
6 | Earthen Gully Plug | 154.8643 |  | 15 | 2197.35 | 337291 | 0 | 3000 | 340291 | 53967 | 0 | 286324 | 15 | 283322 | 3000 | 0 | 286322 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15 | 283322 | 3000 | 0 | 286322
7 | Boulder Gully Plug | 899.0127 |  | 20 | 314 | 280960 | 0 | 4000 | 284960 | 44954 | 0 | 240006 | 21 | 235990 | 4000 | 0 | 239990 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21 | 235990 | 4000 | 0 | 239990
8 | Waste Vier (Moghabandh) | 4038.63 |  | 7 | 217.98 | 177403 | 0 | 702940 | 880343 | 28384 | 0 | 851959 | 7 | 150621 | 701250 | 0 | 851871 | 0 | 0 | 0 | 0 | 0 | 0 |  | 7 | 150621 | 701250 | 0 | 851871
| Sub Total (A) |  |  |  |  | 3428335 | 0 | 987292 | 4415627 | 548533 | 0 | 3867094 | 4192 | 2876732 | 989330 | 0 | 3866062 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4192 | 2876732 | 989330 | 0 | 3866062
B | Drainage treatments
1 | Earthen Dam | 225.495 |  | 1 | 565.6 | 117362 | 0 | 10178 | 127540 | 18778 | 0 | 108762 | 1 | 99000 | 9762 | 0 | 108762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 99000 | 9762 | 0 | 108762
2 | Check Dam | 818575.6 |  | 4 | 4 | 685669 | 0 | 2588633 | 3274302 | 109707 | 0 | 3164595 | 2 | 275450 | 1537200 | 0 | 1812650 | 0 | 2 | 0 | 780000 | 0 | 780000 | 0 | 2 | 275450 | 2317200 | 0 | 2592650
3 | Gabion Structure | 2256.876 |  | 1 | 19.85 | 17895 | 0 | 26904 | 44799 | 2863 | 0 | 41936 | 1 | 26600 | 15281 | 0 | 41881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 26600 | 15281 | 0 | 41881
| Sub Total (B) |  |  |  |  | 820926 | 0 | 2625715 | 3446641 | 131348 | 0 | 3315293 | 4 | 401050 | 1562243 | 0 | 1963293 | 0 | 2 | 0 | 780000 | 0 | 780000 | 0 | 4 | 401050 | 2342243 | 0 | 2743293
C | Climate proofing Activities
1 | Efficient use of water resources | 27771 |  | 35 | 35 | 0 | 0 | 972000 | 972000 | 0 | 215400 | 756600 | 62 | 0 | 729000 | 0 | 729000 | 2 | 0 | 0 | 24000 | 0 | 24000 |  | 64 | 0 | 753000 | 0 | 753000
2 | Soil fertility and productivity enhancement | 4843 |  | 430 | 430 | 692600 | 0 | 1390050 | 2082650 | 166045 | 110555 | 1806050 | 577 | 435500 | 637318 | 0 | 1072818 | 90 | 20 | 0 | 289100 | 0 | 289100 |  | 667 | 435500 | 926418 | 0 | 1361918
3 | Sustainable farming practices | 3014 |  | 400 | 400 | 42000 | 0 | 1163750 | 1205750 | 6720 | 27485 | 1171545 | 391 | 15000 | 542616 | 0 | 557616 | 209 | 0 | 0 | 164075 | 0 | 164075 |  | 600 | 15000 | 706691 | 0 | 721691
4 | Climate risk mitigation measures | 4294 |  | 400 | 400 | 243600 | 0 | 1214100 | 1387700 | 114800 | 0 | 1272900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Sub Total (C) |  |  |  |  | 978200 | 0 | 4739900 | 5648100 | 287565 | 353440 | 5007095 | 1030 | 450500 | 1908934 | 0 | 2359434 | 301 | 20 | 0 | 477175 | 0 | 477175 |  | 1331 | 450500 | 2386109 | 0 | 2836609
D | Landless women & livelihood development |  |  | 16 | 16 | 100360 | 0 | 1214640 | 1315000 | 100360 | 0 | 1214640 | 21 | 0 | 1214640 | 0 | 1214640 | 1 | 0 | 0 | 0 | 0 | 0 |  | 22 | 0 | 1214640 | 0 | 1214640
E | Knowledge managemen t, capacity building, exposure visits and documentation |  |  | 75 | 75 | 0 | 0 | 810000 | 810000 | 0 | 0 | 810000 | 46 | 0 | 371385 | 0 | 371385 | 12 | 3 | 0 | 201062 | 0 | 201062 |  | 58 | 0 | 572447 | 0 | 572447
| Sub Total (D+E) |  |  |  |  | 100360 | 0 | 2024640 | 2125000 | 100360 | 0 | 2024640 | 67 | 0 | 1586025 | 0 | 1586025 | 13 | 3 | 0 | 201062 | 0 | 201062 |  | 80 | 0 | 1787087 | 0 | 1787087
F | Management expenses | [7 empty] | 3113074 |  |  | 3113074 |  |  |  |  | 2191344 | [5 empty] | 151978 | [5 empty] | 2343322
| Sub Total (F) | [7 empty] | 3113074 |  |  | 3113074 |  |  |  |  | 2191344 | [5 empty] | 151978 | [5 empty] | 2343322
4 | Pre CBP expenses
G | Others (Addl. Incentive on successful completion of the project) | [7 empty] | 200000 |  |  | 200000
| Supervision | [5 empty] | 418037 |  | 418037 |  |  | 418037 |  |  |  |  | 373940 | [5 empty] | 0 | [5 empty] | 373940
| Maintenance Fund (50% of shramadan)-FIP | [7 empty] | 675623 |  |  | 675623
| Sub Total (G) | [7 empty] | 1293660 |  |  | 1293660 |  |  |  |  | 373940 | [5 empty] | 0 | [5 empty] | 373940
| Area Treatment (A+B+C+D+E+F+G) |  |  |  |  | 5227461 | 418037 | 8352907 | 20042102 | 1067806 | 353440 | 18620856 | 5293 | 3728282 | 6046532 | 0 | 12340098 | 314 | 25 | 0 | 1458237 | 0 | 1610215 |  | 5607 | 3728282 | 7504769 | 0 | 13950313
Please Note : Any difference is due to rounding off in Sum Totals.

## mgmt exp.
Management Cost
Particular | Expenses upto last reporting period | Expenses during current reporting period | Cumulative Expenses
Details of Expenses Incurred
1.Salaries | 1827250 | 192000 | 2019250
a) Project Manager/Engineer/Community Organiser/Accountant cum Clerk | 1827250 | 151978 | 1979228
b) Woman Coordinator | 0 | 0 | 0
2. Consultancy Charges (CBP/FR Preparation ) | 99048 | 0 | 99048
3. Travelling Expenses/Transportation | 113876 |  | 113876
4. Inauguration Ceremony | 0 | 0 | 0
5. Monitoring Shramdaan | 0 | 0 | 0
6. Exposer Visite | 0 | 0 | 0
7. Office Expenses | 36500 |  | 36500
a. Printing & Stationery | 13670 | 0 | 13670
b. Postage | 0 | 0 | 0
c. rent | 101000 |  | 101000
d. audit fee |  | 0 | 0
e.Computer Expenses | 0 | 0 | 0
f. Misc. (Meeting VWC) Photography | 0 | 0 | 0
Total Administration Expenses | 2191344 | 151978 | 2343322
Amount Received | 2343322 |  | 2343322
Cash Balance | 0 | 0 | 0