## 31.12.24
District: |  | Sidhi
Duration of Report From 24-01-2022 to 31-12-2024
Sl. No | Name of the project | Stage of the Project (CBP/FIP/WDF-CP/SDP/IWMS) | Date of Sanction | Name of Ongoing Project Activities | No. of Mandays Generated | Matterials/Plants/Organic Manure/pest | No. of Waterbodies created | Increase in water storage capacities due to de-sliting | Increase in irrigarion capacity/ Area | Total Labour payment made during the reporting period (in Lakhs) | Total Grant Sanctioned | Total Grant Released (VWC +PIA) | Utilization as on | Remarks if not done
1 | Lurghuti Watershed Project | FIP | 9th, December-2021 | 10 Nos.FP (Farm pond) | 9339 | 131270 | 10 No. | 0 | 0 | 1753534 | 1884806 | 1884804 | 1884804
2 |  |  |  | 750 Nos. SCT | 549 | 4000 | 750 No. | 0 | 0 | 100248 | 104296 | 104296 | 104248
3 |  |  |  | 19 Acre Farm Bund | 1678.5 | 3000 | 19 Acre | 0 | 0 | 293940 | 296983 | 296983 | 296940
4 |  |  |  | 1600 Plant Agroforestry | 124 | 58770 | 1750 Plant | 0 | 0 | 23685 | 82522 | 82521 | 82455
5 |  |  |  | 1600 Plant Horticulture | 185 | 84040 | 1620 Plant | 0 | 0 | 35392 | 120198 | 120197 | 119432
6 |  |  |  | 15 Nos. Gully Plug (Earthen) | 1649.5 | 3000 | 15 No. | 0 | 0 | 283322 | 286324 | 286324 | 286322
7 |  |  |  | 20 Nos. Gully Plug (Boulder) | 1280 | 4000 | 21 No. | 0 | 0 | 235990 | 240006 | 240006 | 239990
8 |  |  |  | 7 Nos. Mogha Bandh | 696 | 701250 | 7 No. | 0 | 0 | 150621 | 851959 | 851959 | 851871
9 |  |  |  | 1 Nos Earthen Dam | 495 | 9762 | 1 No. | 0 | 0 | 99000 | 108762 | 108762 | 108762
10 |  |  |  | 4 Nos Check Dam | 1287 | 2317200 | 2 No. | 0 | 0 | 275450 | 3164595 | 3147795 | 2592650
11 |  |  |  | 1 Nos Gabion Structure | 133 | 15281 | 1 No. | 0 | 0 | 26600 | 41936 | 41936 | 41881
12 |  |  |  | 35 nos Efficient use of water resources | 0 | 753000 | 64 No. | 0 | 0 | 0 | 756600 | 753600 | 753000
13 |  |  |  | 430 nos-Soil fertility and productivity enhancement | 2650 | 926418 | 667No. | 0 | 0 | 435500 | 1806050 | 1443436 | 1361918
14 |  |  |  | 400 nos Sustainable farming practices | 45 | 706691 | 600 No. | 0 | 0 | 15000 | 1171545 | 845015 | 721691
15 |  |  |  | 400 nos Climate risk mitigation measure | 0 | 0 | 0 | 0 | 0 | 0 | 1272900 | 0 | 0
16 |  |  |  | 16 nos Landless women & livelihood development | 0 | 1214640 | 22 No. | 0 | 0 | 0 | 1214640 | 1214640 | 1214640
17 |  |  |  | 75 nos Knowledge management, capacity building, exposure visits and documentation | 0 | 572447 | 58 No. | 0 | 0 | 0 | 810000 | 637000 | 572447
18 |  |  |  | Management Expenses | [6 empty] | 3113074 | 2343322 | 2343322
19 |  |  |  | Other( Additional insentive of completion of the project) | [6 empty] | 200000 | 0 | 0
20 |  |  |  | Supervision cost | [6 empty] | 418037 | 363773 | 373940
21 |  |  |  | Maintenance Fund(50% of Sharamdan) FIP | [6 empty] | 675623 | 0 | 0
|  |  |  | TOTAL | 20111 | 7504769 | 5607 No. | 0 | 0 | 3728282 | 18620856 | 14766369 | 13950313
|  | MF ACCOUNT DEPOSIT AMOUNT | 444730